## Sheet1
Job Desc | Developer | Start | End | Status
Data preparation | Putri | Oct 12 2021 | Oct 13 2021 | Done
Data preprocessing | Wien | Oct 25 2021 | Oct 26 2021 | Done
Modelling | Putri | Oct 25 2021 | Oct 26 2021 | Waiting
Model inference | Wien |  |  | Waiting
Model evaluation | Putri |  |  | Waiting
Prediksi data | Wien |  |  | Waiting
Front-end | Putri |  |  | Waiting
Back-end | Wien |  |  | Waiting
Deployment | Putri |  |  | Waiting
Testing | Wien |  |  | Waiting